## Sheet1
[14 empty] | Rudr Prasad | Rishal Prasad | Ben Ryan | Shamal Prasad | James Chalres | Ahad Ali | Adam Snow
[14 empty] | (Project Manager) | (Business Analyst) | ( ERP Consultant) | (System Engineer) | (Data Analyst) | (QA Engineer) | (Training Specialist)
[14 empty] | 36939 | 43411 | 36939 | 43411 | 43411 | 43411 | 24052
[14 empty] | 17.7591 | 20.8707 | 17.7591 | 20.8707 | 20.8707 | 20.8707 | 11.5635
Assemble team | 1 | 2 | 3 | 2 |  | 2
Perform Stakeholder Analysis | 7 | 10 | 13 | 10 |  | 10
Define Project Scope | 1 | 2 | 3 | 2 |  | 2 | [5 empty] | working hours | 2080
Project Charter Development and Approval | 8 | 11 | 13 | 10.8333 |  | 11
Kick Off Meeting | 1 | 2 | 3 | 2 |  | 2
Requirements Analysis | 2 | 3 | 4 | 3 |  | 3 | [7 empty] | Activities | Responsible | Total Hours | Pay Rate | Overhead | Personal Time | Resources |  |  |  | Total Cost Per Phase
WBS Creation | 3 | 4 | 5 | 4 |  | 4 | [6 empty] | 8 | [6 empty] | Human Resource | Facilities | Equipments | Materials |  |  | Activities | Time Frame
Create Resource Budget | 12 | 13 | 19 | 13.8333 |  | 14 | [7 empty] | Inception | [12 empty] | First Financial Quarter | Second Financial Quarter | Third Financial Quarter | Fourth Financial Quarter
Statement Of Work | 4 | 5 | 8 | 5.3333 |  | 5 | [5 empty] | 2 |  | Assemble team | Project Manager | 16 | 17.76 | 1.2 | 1.15 | 392.1408 | 30 | 10 | 5 | 437.1408 |  | Assemble team | 437.1408
Risk and Change Register | 8 | 9 | 10 | 9 |  | 9 | [5 empty] | 12 |  | Perform Stakeholder Analysis | Project Manager | 80 | 17.76 | 1.2 | 1.15 | 1960.704 | 30 | 10 | 15 | 2015.704 |  | Perform Stakeholder Analysis | 2015.704
Review and Contact Potential Vendor | 7 | 9 | 11 | 9 |  | 9 | [5 empty] | 2 |  | Define Project Scope | Project Manager | 16 | 17.76 | 1.2 | 1.15 | 392.1408 | 10 | 10 | 5 | 417.1408 |  | Define Project Scope | 417.1408
Identify ERP Modules | 5 | 7 | 8 | 6.8333 |  | 7 | [5 empty] | 14 |  | Project Charter Development and Approval | Project Manager | 88 | 17.76 | 1.2 | 1.15 | 2156.7744 | 12 | 10 | 5 | 2183.7744 |  | Project Charter Development and Approval | 2183.7744
Create Simulation Environment | 10 | 12 | 15 | 12.1667 |  | 12 | [5 empty] | 2 | [7 empty] | 4901.76 | 82 | 40 | 30 | 5053.76 |  | Kick Off Meeting | 447.1408
Create Data Sample | 7 | 8 | 10 | 8.1667 |  | 8 | [5 empty] | 3 |  | Planning | [11 empty] | Requirements Analysis | 719.2144
Simulate ERP System and fit gap analysis with SME | 30 | 40 | 52 | 40.3333 |  | 40 | [7 empty] | Kick Off Meeting | Project Manager | 16 | 17.76 | 1.2 | 1.15 | 392.1408 | 30 | 10 | 15 | 447.1408 |  | WBS Creation | 948.6192
Configure ERP System Modules | 20 | 24 | 31 | 24.5 |  | 25 | [5 empty] | 4 |  | Categorize Requirements | Business Analyst | 24 | 20.87 | 1.2 | 1.15 | 691.2144 | 13 | 10 | 5 | 719.2144 |  | Create Resource Budget | 3259.6672
Transfer Data | 14 | 20 | 24 | 19.6667 |  | 20 | [5 empty] | 7 |  | WBS Creation | Business Analyst | 32 | 20.87 | 1.2 | 1.15 | 921.6192 | 12 | 10 | 5 | 948.6192 |  | Statement Of Work | 1010.352
Integrate ERP system with Existing System | 15 | 21 | 23 | 20.3333 |  | 20 | [5 empty] | 7 |  | Resource Budget Creation | Business Analyst | 112 | 20.87 | 1.2 | 1.15 | 3225.6672 | 12 | 8 | 14 | 3259.6672 |  | Risk and Change Register | 2105.6432
Create Test Cases | 12 | 15 | 21 | 15.5 |  | 16 | [5 empty] | 5 |  | Statement Of Work | Project Manager | 40 | 17.76 | 1.2 | 1.15 | 980.352 | 10 | 10 | 10 | 1010.352 |  | Review and Contact Potential Vendor | 1829.6336
System Testing | 20 | 23 | 27 | 23.1667 |  | 23 | [5 empty] | 7 |  | Risk and Change Register | Business Analyst | 72 | 20.87 | 1.2 | 1.15 | 2073.6432 | 10 | 8 | 14 | 2105.6432 |  | Identify ERP Modules | 1259.1669 | 503.6667
User Acceptance testing | 20 | 25 | 29 | 24.8333 |  | 25 | [5 empty] | 6 |  | Review and Contact Potential Vendor | ERP Consultant | 72 | 17.76 | 1.2 | 1.15 | 1764.6336 | 20 | 20 | 25 | 1829.6336 |  | Create Simulation Environment |  | 3914.8576
User Training Material Creation | 10 | 16 | 19 | 15.5 |  | 16 | [5 empty] | 5 | [7 empty] | 10049.2704 | 107 | 76 | 88 | 10320.2704 |  | Create Data Sample |  | 2893.2384
User Training | 10 | 14 | 18 | 14 |  | 14 | [5 empty] | 7 |  | Prototyping | [10 empty] | 9586.192 | Simulate ERP System and fit gap analysis with SME |  | 9586.192
ERP System Phased Deployment | 24 | 30 | 36 | 30 |  | 30 | [5 empty] | 7 |  | Identify ERP Modules | System Engineer | 56 | 20.87 | 1.2 | 1.15 | 1612.8336 | 30 | 50 | 70 | 1762.8336 | 6460.12 | Configure ERP System Modules |  | 2842.4528 | 3617.6672
Project Handover | 2 | 3 | 5 | 3.1667 |  | 3 | [5 empty] | 3 |  | Create Simulation Environment | System Engineer | 96 | 20.87 | 1.2 | 1.15 | 2764.8576 | 50 | 750 | 350 | 3914.8576 |  | Transfer Data |  |  | 5158.096
[12 empty] | 7 |  | Create Data Sample | Data Analyst | 64 | 20.87 | 1.2 | 1.15 | 1843.2384 | 50 | 650 | 350 | 2893.2384 |  | Integrate ERP system with Existing System |  |  | 5283.096
|  |  |  | 50 | [9 empty] | Simulate ERP System and fit gap analysis with SME | System Engineer | 320 | 20.87 | 1.2 | 1.15 | 9216.192 | 100 | 150 | 120 | 9586.192 |  | Create Test Cases |  |  | 4036.4768
|  |  |  | 41 | [7 empty] | 12 | [7 empty] | 15437.1216 | 230 | 1600 | 890 | 18157.1216 |  | System Testing |  |  | 5799.3104
|  |  |  | 30 | [7 empty] | 8 |  | Implementation | [11 empty] | User Acceptance testing |  |  |  | 7255.12
|  |  |  | 16 | [7 empty] | 70 |  | Configure ERP System Modules | System Engineer | 200 | 20.87 | 1.2 | 1.15 | 5760.12 | 50 | 400 | 250 | 6460.12 |  | User Training Material Creation |  |  |  | 2991.9584
|  |  |  | 30 | [7 empty] | 50 |  | Transfer Data | Data Analyst | 160 | 20.87 | 1.2 | 1.15 | 4608.096 | 50 | 250 | 250 | 5158.096 |  | User Training |  |  |  | 3086.7136
|  |  |  | 31 | [7 empty] | 41 |  | Integrate ERP system with Existing System | System Engineer | 160 | 20.87 | 1.2 | 1.15 | 4608.096 | 75 | 300 | 300 | 5283.096 |  | System Phased Deployment |  |  |  | 8012.144
[20 empty] | 14976.312 | 175 | 950 | 800 | 16901.312 |  | Project Handover |  |  |  | 643.2112
|  |  |  | 14 | [9 empty] | Testing | [11 empty] | Hardware Cost |  | 833.34 | 833.33 | 833.33
|  |  |  | 16 | [9 empty] | Create Test Cases | QA Engineer | 128 | 20.87 | 1.2 | 1.15 | 3686.4768 | 50 | 50 | 250 | 4036.4768 |  | Software Licencing |  | 53460 | 53460 | 53460
|  |  |  | 40 | [7 empty] | 30 |  | System Regression Testing | System Engineer | 184 | 20.87 | 1.2 | 1.15 | 5299.3104 | 50 | 200 | 250 | 5799.3104 |  | Contingency Fund | 1215.65 | 1215.65 | 1215.65 | 1215.65
|  |  |  | 5 | [7 empty] | 16 |  | User Acceptance testing | QA Engineer | 200 | 20.87 | 1.2 | 1.15 | 5760.12 | 450 | 645 | 400 | 7255.12 |  | Total Cost Per Financial Quarter | 17848.8473 | 75249.3975 | 79403.6264 | 77498.1272
|  |  |  | 273 | 9.1 | [6 empty] | 30 | [7 empty] | 14745.9072 | 550 | 895 | 900 | 17090.9072
[12 empty] | 31 |  | Transition | [14 empty] | Total Cost of Project | 249999.9984
[12 empty] | 14 |  | User Training Material Creation | Training Specialist | 128 | 11.56 | 1.2 | 1.15 | 2041.9584 | 50 | 200 | 700 | 2991.9584
[14 empty] | User Training | Training Specialist | 112 | 11.56 | 1.2 | 1.15 | 1786.7136 | 400 | 300 | 600 | 3086.7136
[12 empty] | 16 |  | ERP System Phased Deployment | System Engineer | 240 | 20.87 | 1.2 | 1.15 | 6912.144 | 500 | 450 | 150 | 8012.144
[12 empty] | 40 |  | Project Handover | Project Manager | 24 | 17.76 | 1.2 | 1.15 | 588.2112 | 10 | 20 | 25 | 643.2112
[20 empty] | 11329.0272 | 960 | 970 | 1475 | 14734.0272
[20 empty] | Total Resource Cost |  |  |  | 82257.3984
[20 empty] | Hardware Maintenance Cost |  |  |  | 2500
[20 empty] | Software and Licensing Cost |  |  |  | 160380
[20 empty] | Contingency Funds |  |  |  | 4862.6
[20 empty] | Final Cost Of Project |  |  |  | 249999.9984
Summary Budget of ERP System of ANZ Bank
[27 empty] | Task | Cost
Inception
[27 empty] | Fully Loaded Labour | 4901.76
[27 empty] | Facility | 82
[27 empty] | Equipment | 40
[27 empty] | Material | 30
[8 empty] | per user per month | for 9 months | 15 users | [16 empty] | Phase Total | 5053.76
[7 empty] | Dynamics 365 Business Central Essentials | 200 | 9 | 18 | 32400 | [15 empty] | Planning
[7 empty] | Dynamics 365 Customer Service | 100 | 9 | 18 | 16200 | [15 empty] | Fully Loaded Labour | 10049.2704
[7 empty] | Dynamics 365 Human Resources | 270 | 9 | 18 | 43740 | [15 empty] | Facility | 107
[7 empty] | Dynamics 365 Finance | 420 | 9 | 18 | 68040 | [15 empty] | Equipment | 76
[11 empty] | 160380 | [15 empty] | Material | 88
[27 empty] | Phase Total | 10320.2704
Prototyping
[27 empty] | Fully Loaded Labour | 15437.1216
[27 empty] | Facility | 230
[27 empty] | Equipment | 1600
[27 empty] | Material | 890
[27 empty] | Phase Total | 18157.1216
Implementation
[27 empty] | Fully Loaded Labour | 14976.312
[27 empty] | Facility | 175
[27 empty] | Equipment | 950
[27 empty] | Material | 800
[27 empty] | Phase Total | 16901.312
Testing
[27 empty] | Fully Loaded Labour | 14745.9072
[27 empty] | Facility | 550
[27 empty] | Equipment | 895
[27 empty] | Material | 900
[27 empty] | Phase Total | 17090.9072
Transition
[27 empty] | Fully Loaded Labour | 11329.0272
[27 empty] | Facility | 960
[27 empty] | Equipment | 970
[27 empty] | Material | 1475
[27 empty] | Phase Total | 14734.0272
[27 empty] | Total Loaded Labour Cost | 82257.3984
[27 empty] | Hardware Cost | 2500
[27 empty] | Software Licensing Cost | 160380
[27 empty] | Contingency Funds | 4862.6
[27 empty] | Total Cost Of Project | 249999.9984